## Phase-2 Features
Wealthyvia Phase-2
Section | Feature Item | Time | Status | Developer
Chart Upload - Release 1
Admin | Facility to Upload the CSV File for each product. Provide Validations to each field / column. Make sure dupliocate racords are not entered as per date. After data uploaded, display successful records and failed records due to validations. Contact Priyanka Bhanavase for Excel Upload program. Add new link in navigation leftsidebar, Product Charts. When clicked on the link, Admin will land on a CSV upload page. There will be a dropdown of products. After csv is uploaded, Admin can see good and bad records. Below that, show the charts. Collection name: productRates { _id: xxx, productName: '5GCPM', indexName: 'Nifty MidCap', rates : [ {date: 01-07-2020, productRate: 101.1, indexRate: 101.5 } {date: 02-07-2020, productRate: 101.1, indexRate: 101.5 } {date: 03-07-2020, productRate: 101.1, indexRate: 101.5 } ], createdBy: user_id, createdAt : Insert Timestamp, updateLog: [ {updatedBy: user_id, updatesAt: current timestamp} ] | 16
Admin | Use Bootstrap tabs and create tabs for 1M to Max. When selected any tab, show only that duration chart. | 8
Website | Display Charts for Products side on Website On product url https://wealthyvia.com/offerings/5gcpm Give 2 tabs below blue color block : Overview & Performance Performance tab will have entire line chart. Default will be Max. First develop the chart solution for Max. Then we will add tabs for 1M, 3M, 6M, 1Y, 2Y and Max. | 8
Admin | Create New Product with name 'Free Research Reports' Upload Research reports for this product, in PDF format. Website side, in Articulation Menu, add new submenu "Free Research Reports' Create new url 'free-research-reports' Page design will be provided by Pritam. Use new API to get the research report for this new product. | 12
Distributor Onboarding - Release 2
Website | Distributor Onboarding Form. Develop form as per google form. Design should be like Signup form. All validations and Insert must work. | 8 | Done | Prince
Website | After successful Insert, send notification to Admin and to User. | 4 |  | Monika
Admin | List of Distributors Registrations View, Edit, Delete, Approve, Reject | 4 | Done | Prince
Admin | Distributor Profile View | 4 | Done | Prince
Admin | When distributor profile is approved, status changes to 'Approved' When distributor profile is Rejected, status changes to 'Rejected' | 2 | Done | Prince
Admin | When distributor profile is approved, User Credentials of the Users are created and Automatic welcome email is sent to user and Admin. The role of "distributor" is assigned. | 2 | Done | Prince
Distributor | Setup New Distributor Project. Copy Admin folder and rename it as distributor. At the time of Login, check if the Role is "distributor". | 4 | YTS | Monika
Distributor | When Distributor logins first time, force the user to change the password. Contact Omkar. Distributor should not be able to see Dashboard & left sidebar. After Password is changed, send distributor to Profile Form. When this profile form is showed, that time also left sidebar is not shown. | 1 | YTS | Monika
Distributor | Distributor Profile Form, for status ="Approved" The profile form will have original fields shown at the time of registration + following fields - Pan No - Aadhar No - GST no if taken Bank details - Bank Acc name : - Bank Name - Branch Name - IFSC code - MICR code | 3 | YTS | Monika
Distributor | In Left Sidebar, Following links are visible - My Profile - My direct clients - My Tools - My Sub Franchise - My Earnings - Create Client | 8 | YTS | Monika
Distributor | My Profile View Page Show Left sidebar at this time. - Edit & Delete icons Following information - Pan No - Aadhar No - GST no if taken. Bank details - Bank Acc name : - Bank Name - Branch Name - IFSC code - MICR code | 16 | YTS | Monika
Distributor | Direct Clients ' - Create Direct Clients (You don't need to provide any specificform to add new client. We will modify the Singup form. Add one field - Referred By. This will be autocomplete field. Add Distrubutor Code in this field.) - List of Clients (Special API for this list. Fetch only those clients from USER/Client Tables where Referred By Code = Distributor Code) | 24 | YTS | Monika
Distributor | Distributor can refer SubFranchise. SubFranchise will fill up the same form "Become a Partner" from website. One more field "Referred By" where SubFranchise must add Distributor code. System will verify this valid code and then form gets submitted. Admin will see the details of this Distributor who referred the SubFranchise. Distributor can see the list of his SubFranchise referred to System. Also the total number of clients and total AUM for each SubFranchise will be shown in the list. | 8 | YTS | Monika
Admin | Earnings Report (Sample format to be given by Pritam sir) | 8 | YTS | Monika
Distributor | Tools - Video URLS of trainings (Show YouTube Videos) - Presentations - Docs ppts to download | 8 | YTS | Prince
Admin | Tools upload Client code addition Client attributes : Capital Invested , start date and end date and Fees addition | 8 | YTS | Prince
Admin | Research on Auto-Download the CSV file from source and upload it automatically. This is Research oriented work, must be done after successful manual upload. Low Priority, to be done at the end. | x

## Sheet1
|  |  | Ashish Naik |  |  | Address
|  |  | Ph: +91 99233 93733 |  |  | xxxxxxxxxxxxxxxxxxxxxxxxxx
|  |  | Email: ashish.naik@iassureit.com |  |  | xxxxxxxxxxxxxxxxxxxxxxxxxx
|  |  | DOB: |  |  | Field1
|  |  | GST: |  |  | Field2
Earning Table
|  |  |  | Cap Inv | My Share
| Client-1 | 1 Crore |  | 2 | 1
| Client-2 | 2 Crore |  | 4 | 2
| Client-3 | 1.5 Crore |  | 3 | 1.5
| Client-4 | 4 Crore |  | 8 | 4
| Client-5 | 10 Crore |  | 20 | 10
18.5