## Deliverables
iAssure International Technologies Pvt Ltd www.iassureit.com ¦ ashish.naik@iassureit.com ¦ +91-99233 93733
Project Name
Customer
Project Manager
Planned Start Date
Planned End Date
Milestone / Deliverable | Due Date
Release 1: Chart Upload | 2020-07-30
Release 2: Distributor Onboarding

## Team Composition
iAssure International Technologies Pvt Ltd www.iassureit.com ¦ ashish.naik@iassureit.com ¦ +91-99233 93733
Project Name
Customer
Project Manager
Planned Start Date
Planned End Date
Team Members Name | Role
Monika | Developer
Prince | Developer
Anuja | Tester

## WBS
iAssure International Technologies Pvt Ltd www.iassureit.com ¦ ashish.naik@iassureit.com ¦ +91-99233 93733
Section | Feature / Task | Total Efforts (In Hours) | Size (Points) | Status | Allocated To | Planned Start Date | Planned Finish Date | Actual Start Date | Actual Finish Date | Schedule Adherence
Release 1: Chart Upload
Admin | Facility to Upload the CSV File for each product. Provide Validations to each field / column. Make sure duplicate records are not entered as per date. After data uploaded, display successful records and failed records due to validations. | 16 | 8 | WIP | Monika | 2020-07-18 | 2020-07-20
Admin | Use Bootstrap tabs and create tabs for 1M to Max. When selected any tab, show only that duration chart. | 8 | 4 | YTS | Monika | 2020-07-22 | 2020-07-22
Website | Display Charts for Products side on Website Performance tab will have entire line chart. Default will be Max. First develop the chart solution for Max. Then we will add tabs for 1M, 3M, 6M, 1Y, 2Y and Max. | 8 | 4 | YTS | Monika | 2020-07-21 | 2020-07-21
Admin | Create New Product with name 'Free Research Reports' Upload Research reports for this product, in PDF format. Website side, in Articulation Menu, add new submenu "Free Research Reports' Create new url 'free-research-reports' | 12 | 6 | YTS | Monika | 2020-07-23 | 2020-07-23
| Testing of the Release 1 functionalities | 12 | 6 | YTS | Anuja | 2020-07-21 | 2020-07-25
| Defect fixing and rework | 8 | 4 | YTS | Monika | 2020-07-24 | 2020-07-27
| Demo to Customer | 2 | 1 | YTS | Anuja | 2020-07-30 | 2020-07-30
Release 2: Distributor Onboarding
Website | Distributor onboarding form | 8 | 4
Admin | List of registrations | 4 | 2
Admin | Create Login Credentials for Distributor with Email as his login ID and Default password. Send these credentials and login link via email to Distributor with ability to Approve or Reject. Appropriate notifications to be generated. | 8 | 4
Distributors | When Distributor logins first time, force the user to change the password. Redirect to Dirstibutor Dashboard. Following links are visible - My Profile - My direct clients - My Tools - My Sub Franchise - My Earnings - Create Client | 8 | 4
Distributors | My Profile - Insert, View Page, Edit & Delete - Display Registration form Information + following information - Bank Acc name : - Pan No - Aadhar No - Bank Name - Branch Name - IFSC code - MICR code - GST no if taken | 16 | 8
Distributors | Direct Clients - Create Direct Clients - List of Clients - Edit Client Info - Delete Client (Logical Deletion) - List of Deleted Clients - Recover Client from Deleted Clients List | 24 | 12
Distributors | Tools - Video URLS of trainings (Show YouTube Videos) - Presentations - Docs ppts to download | 8 | 4
Distributors | Distributor can refer SubFranchise. SubFranchise will fill up the same form "Become a Partner" from website. One more field "Referred By" where SubFranchise must add Distributor code. System will verify this valid code and then form gets submitted. Admin will see the details of this Distributor who referred the SubFranchise. | 8 | 4
Admin | Earnings report (Details to be discussed)
Admin | Tools upload Client code addition Client attributes : Capital Invested , start date and end date and Fees addition | 8 | 4
Admin | Research on Auto-Download the CSV file from source and upload it automatically. This is Research oriented work, must be done after successful manual upload. Low Priority, to be done at the end.

## Sheet2 (hidden)
Done
WIP
YTS
On Hold